## Slide 1
Module 3 The project cycle

## Slide 2
Module 3 Session 1 Context and the project cycle

## Slide 3: Learning objectives
• To describe the factors that influence analysis in humanitarian contexts
• To demonstrate how to use the Sphere handbook to analyse the humanitarian context effectively
• To describe the steps in the project cycle

## Slide 4: Mitch case study

## Slide 5: Context issues
• Economic, social, political
• Climate and geography
• Organisational
• Cultural, psychological
• Gender issues
• Human rights issues
• Societal norms and local coping capacities

## Slide 6: Information constraints
Attempts to gather and manage data and information
Low priority for information systems
Lack of skill and experience
Quantitative bias
Poor feedback to collector and community
Low involvement

## Slide 7: The project cycle
Monitor Evaluate
Plan, design Redesign
Assess
Implement
Analyse
Disaster
ADVOCACY

## Slide 8
Module 3 Session 2 Using Sphere in assessments

## Slide 9: Learning objectives
• To define where assessment happens in the project cycle
• To decribe what bias is and how it might influence assessment
• To define the purpose of assessment in the humanitarian response
• To describe how standards and checklists can enhance assessment
• To describe the role of key indicators in assessment
• To recognise that: - the project cycle is iterative - assessment is a first stage

## Slide 10: The project cycle
Monitor Evaluate
Plan, design Redesign
Assess
Implement
Analyse
Disaster
ADVOCACY

## Slide 11: Balancing speed and accuracy in assessments
1 SPEED
3 UTILITY
2 ACCURACY
Utility of assessment findings
Accuracy Time
= f
InterWorks

## Slide 12: The assessment / monitoring process
Identify information,
needs, resources
Collect data
Analyse,
interpret
Report
conclusions
Design/modify
response
InterWorks/UNHCR

## Slide 13: Domistan map
South Town
Industrial
Centre
Plateau
Delta
Sea
N
S
E
W
CAPITAL
Mountains
North Town
DOMISTAN
Neighbouring country

## Slide 14: Common standard 2
Initial assessment “Assessments provide an understanding of the emergency situation and a clear analysis of threats to life, dignity, health and livelihoods to determine, in consultation with relevant authorities whether an external intervention is required and, if so, the nature of the response.”

## Slide 15: Indicators
• ‘Signals’ that show whether a standard has been attained. • They provide a way of measuring and communicating both the impact, or result, of programmes as well as the process, or methods, used. • The indicators may be qualitative or quantitative.

## Slide 16: Using Sphere to mitigate bias
Wider community context
“ To a person with a hammer in their hand every problem looks like a nail ”
Organisational mandate or specialty
BIAS
Resources
Humanitarian needs

## Slide 17: How to reduce bias
Joint assessments
Triangulation • varing techniques • indicators of same event • info sources • team composition
Coordination
Adherence to baseline standards
InterWorks/UNHCR

## Slide 18: Assessment standards in Sphere
Common standard 2: initial assessment
Checklists for initial assessments:
1 Water supply, sanitation and hygiene promotion
2 Food security, nutrition and food aid
3 Shelter, settlement and non-food items
4 Health services

## Slide 19
Module 3 Session 3 Using Sphere in analysis

## Slide 20: Learning objectives
• To demonstrate how to use the Sphere handbook in problem analysis.
• To define the purpose of analysis and where it happens in the project cycle.
• To define how the Sphere handbook can enhance the quality of analysis.
• Identify practical analysis techniques and tools to use with the Sphere handbook.

## Slide 21: The project cycle
Monitor Evaluate
Plan, design Redesign
Assess
Implement
Analyse
Disaster
ADVOCACY

## Slide 22: Some analytical ‘lenses’
• Social, political and economic
• Gaps in available resources
• Use and control of resources
• Demographic compositions
• Technical and sectoral
• Capacities and vulnerabilities

## Slide 23: Capacity and vulnerability analysis
Vulnerabilities
Capacities
Physical/ Material
Elderly people and children - difficult to get food aid
Food and income from local farming
Social/ Organisational
HIV / AIDS: demographic age shift
Tradition of family care
Motivational/ Attitudinal
Mass bereavement
Commitment to education

## Slide 24: The problem tree
Emergency
Distress
Effects
U5 mortality
Focal problem
Causes
Measles
Diarrhoea
Malaria
Low vaccination rate
Hygiene
Not enough water
Mosquitoes
No bed nets
No latrines

## Slide 25
Module 3 Session 4 Sphere and programme planning

## Slide 26: Learning objectives
• To demonstrate how to use the Sphere handbook - in project planning - with a logical framework
• To list the key principles of project planning and identify where it happens in the project cycle
• To demonstrate how to use a gap identification chart in coordinating project planning

## Slide 27: The project cycle
Monitor Evaluate
Plan, design Redesign
Assess
Implement
Analyse
Disaster
ADVOCACY

## Slide 28: Domistan case study
Excess mortality and life without dignity
Disposable, non-portable assets being sold
CAUSES
EFFECTS
EFFECTS
EFFECTS
Psychosomatic illnesses
Out - migration
Political statements by local leaders blaming opposition
Hysteria, giving away babies to foreign press

## Slide 29: Water and sanitation problem tree
Lack of dignity and High mortality
Malnutrition
Rubbish
Unclean
Overcrowding
No control
Insufficient
quantity
Not enough
units
Political problems - keeping migrants
away from host population in a small space
No maintenance
Diarrhoea
Malaria
No bed nets
Vectors
Hygiene
problems
• slaughtering
• no soap
• no space
Poor toilets
Inadequate
water

## Slide 30: Shelter problem tree
High mortality
Lack of dignity
Poor
vaccination
coverage
Overcrowding
in shelters
Cold damp
weather
Improper
drugs
Measles
Acute respiratory
infections
Hard shelter
contaminated
Politics of keeping displaced people
away from host population
Few temporary
shelters
Improper
clothing

## Slide 31: Health problem tree
High mortality
Traumatic injury
Improper
drugs
Poor
drugs
Poor
vaccination
coverage
Fuel wood
far away
Too few
doctors
Communal washing
far away
Not enough
clinics
Population
doubles
in town
Population
displacement
Political
crisis
War
economy
Historical situation
of poor wealth sharing
Land
tenure
Measles
ARI
Diarrhoea
Malaria
Violence
against
minorities
Violence
against
women
Inadequate
clinics

## Slide 32: Nutrition problem tree
Washing
facilities
too far
away
Fuel is in
distant
lowlands
Disease burden
Lack of dignity
Malnutrition
Inability to
prepare food
Improper food basket
• calories
• palatability
Changed social
environment
Micro-
nutrient
Deficiencies
(pellagra)
Theft en route
to city
Few other
assets
War economy
No
blended
food
Donor politics, fatigue
low strategic value
Insecurity in lowlands
Low purchasing
power, low
income for
sold rations
No
stoves
Violence
against
women
Women take
too much time
collecting fuel
No local purchases
Pipeline
delays
Rapid growth, Too much debt, devalued currency
Hyper inflation

## Slide 33: Food security problem tree
Hyper
inflation
Inability to
prepare food
Improper food basket
• calorific value
• palatability
Women
spending
too much
time
collecting
firewood
Fuel far away
in insecure
farmlands
Stoves
Low
purchasing
power
Theft en route
War economy
Few other
assets
Pipeline
delays
Transporter
contractual
problems
• lost paperwork
• auditors
• unpaid invoices
No local
purchases
Security in
lowlands
Lack of dignity and Malnutrition

## Slide 34: Programme planning…
‘Programme planning should be a coordinated effort to fulfil a strategy resulting in desired impacts – a life with dignity for all programme participants’

## Slide 35: A coordination tool
Local Community
RESOURCES
State Government
F.O.O.D.
Red Cross
Domistani Sisters
Donor X
Gap Identification Worksheet
Roads
Food
Water
Security
Shelter
Blankets
Medicines
Tracing
UNHCR
NEEDS

## Slide 36: Logical framework
Impact
Effect, or outcome, or objective
Expected output
Activities
Inputs
Objectively verifiable indicators
Risks, hypothesis, assumptions
Narrative description
Sources of information
Key indicators
Standards
Charter
Guidance notes

## Slide 37: Summary
• Select indicator and justify
• Determine activities
• Determine levels of response
• Clarify what programmes can achieve
• Use a common language to enable coordination

## Slide 38
Module 3 Session 5 Sphere and Monitoring and Evaluation

## Slide 39: Learning objectives
• To select and apply priority key indicators from the Sphere handbook to a specific project
• To discuss and contrast key elements of monitoring and evaluation
• To describe how to set up a monitoring system for a humanitarian project
• To select, adapt and `operationalise’ indicators for a specific project
• To describe how emergency situations constrain monitoring and evaluation

## Slide 40: The project cycle
Disaster
Monitor Evaluate
Plan, design Redesign
Assess
Implement
Analyse
ADVOCACY

## Slide 41: Monitoring
information
A continuous and systematic process of recording, collecting, measuring, analysing and communicating

## Slide 42: What information?
Progress of project implementation
Developments in the project environment
Analysis of interaction between: project and environment

## Slide 43: Guiding principles for monitoring
• Focuses on minimal information required for each level of responsibility
• Includes all forms of communication: verbal, written, formal, informal
• Uses participatory methods
• Creates an obligation to act on operational and strategic implications of information received

## Slide 44: Evaluation...
• improve policy and practice • enhance accountability
Systematic and impartial examination of humanitarian action intended to draw lessons to:

## Slide 45: The difference between M&E
“There is no universal agreement as to what ground the terms monitoring, review and evaluation should cover (…). The important thing is to gain agreement on basic principles and definitions with those agencies and individuals you work with directly.” (B. Broughton & J. Hampshire)
Monitoring and evaluation are different processes but can merge

## Slide 46: Indicators
“ … a small set of data, ... usually easy or cost-effective to collect, highly correlated with other data, and from which much useful and trustworthy conclusions can be derived quickly.” (UNDRO)

## Slide 47: Operationalise indicators
• Where will the data be collected from?
• Who will collect it?
• When will it be collected, and how frequently?
• How will the data be collected and stored?
• Who will analyse the data?
• How will it be reported?
• How will management decisions be made based on the monitoring report?

## Slide 48: What Sphere says about M&E
• Common standard 5:
• Common standard 6:
Monitoring
Evaluation

## Slide 49
Module 3 Session 6 Beyond the project cycle

## Slide 50: Learning objectives
• To identify which of those issues could be addressed by using the Sphere handbook
• To list 10 critical issues facing the humanitarian system

## Slide 51: 2002 ALNAP 10 performance issues
1 Human resources
2 Preparedness
3 Coordination
4 Participation and capacity building
5 Indigenous coping strategies
6 Gender equality
7 Targeting
8 Relief to development
9 Protection
10 Results-based planning

## Slide 52: Barriers to coordination
• Threat to autonomy
• Competition for resources
• Many organisations
• Different measures of success

## Slide 53: What is accountability?
“ The responsibility to demonstrate to stakeholders, foremost of whom are disaster-affected people, that humanitarian assistance complies with agreed standards.” (Sphere 2000)

## Slide 54: Rwanda case study

## Slide 55: BREAK!